## 1
Task ID | Task Name | Predecessor
1 | Erect Formwork | NULL
2 | Install Rebar | 1
3 | Pour Concrete | 2
4 | Retract Formwork | 3
5 | Cure Concrete | 3

## 2
Task ID | Component | Activity | Required_Resources | Productivity
1 | Wall Panel | Survey panel location | Survey crew | 1 panel/T(8,12,10) min
2 | Wall Panel | Lift wall panel | Crane crew | 1 panel/T(9,15,12) min
3 | Wall Panel | Connect wall panel | Frame crew, Crane crew | 0.25 connections/min
4 | Slab | Install rebar slab | Reinforcement crew | 29 C.S.F./day
5 | Slab | Pour concrete slab | Concrete crew | 55 ㎥/day
6 | Foundation | Erect formwork foundation | Formwork crew | 300 s.f./day
7 | Foundation | Install rebar foundation | Reinforcement crew | 2.1 ton/day
8 | Foundation | Pour concrete foundation | Concrete crew | 11 ㎥/day

## 3
Resource | Quantity
Frame crew | 1
Formwork crew | 1
Survey crew | 1
Crane crew | 1
Drywall crew | 1
Reinforcement crew | 1
Concrete crew | 1
Insulation crew | 1